## Roadmap
Phase | Timeline (Weeks) | Primary Focus | AI-Free Deliverables | AI-Included Deliverables | Owner
Discovery | 1-4 | Baseline assessment | Architecture, data inventory | AI readiness evaluation | Consultant
Foundation | 4-8 | Establish cloud/data foundations | ALZ, contracts, gateway | Feature store skeleton, model registry | Cloud/Data Lead
Modernization | 8-16 | Refactor and deploy | Component library, APIs | RAG pilots, eval harness | Dev Lead
Intelligence | 16-24 | Operational AI | Monitoring, alerts | Agents, predictive scaling | AI Lead
Optimization | 24-32 | Governance & FinOps | Dashboards, KPIs | Continuous learning, cost optimization | PMO